## Sheet1
Project plan for Dawam web Portal and Backend APIs
Module | No.of days | Estimate hours (Backend API and web portal)
Database Schema Design/ER Diagram for Database structure | 9 | 81
Project Setup and Development Server setup for Backend API design | 3 | 27
Authentication (Login/Signup/ Add Phone numebr ) | 3 | 27
Add phone number: all country picker and accordingly country code | 4 | 36
Verify Account | 3 | 27
Home screen | 5 | 45
Backend APIs for GPS, Face and Voice recognition implementation in mobile app | 5 | 45
Location | 3 | 27
My Requests: Calendar library implementation | 5 | 45
My profile | 4 | 36
My Employees | 4 | 36
My Supervisors | 4 | 36
My Admin-Location | 4 | 36
Log out | 1 | 9
API / Web portal Testing | 8 | 72
Total | 56-60 working days | 504 (Hours)